## Action Items
# | Phase | Action | Owner | Team | Priority | Status | Started At | Target By | Completed At | Notes
ACT-001 | Triage | Confirm alert is genuine — check core-router-edge-01 directly | Daniel Ortega | SRE | P1 | Open |  | T+2
ACT-002 | Triage | Assess blast radius — identify all affected services and users | Daniel Ortega | SRE | P1 | Open |  | T+3
ACT-003 | Triage | Open Zoom bridge and Slack incident channel | Daniel Ortega | SRE | P1 | Open |  | T+5
ACT-004 | Triage | Page all immediate-notify stakeholders | Daniel Ortega | SRE | P1 | Open |  | T+5
ACT-005 | Comms | Send Initial Incident Notification email (Template 1) | Carlos Mendez | Engineering Leadership | P1 | Open |  | T+5
ACT-006 | Comms | Post Slack message to incident channel | Carlos Mendez | Engineering Leadership | P1 | Open |  | T+5
ACT-007 | Comms | Send War Room Established email (Template 2) | Carlos Mendez | Engineering Leadership | P1 | Open |  | T+10
ACT-008 | Comms | Send T+30 Status Update email (Template 3) | Carlos Mendez | Engineering Leadership | P1 | Open |  | T+30
ACT-009 | Diagnosis | Run initial Network health check on core-router-edge-01 | Fatima Al-Hassan | Platform Engineering | P1 | Open |  | T+10
ACT-010 | Diagnosis | Collect logs from affected CI and downstream services | Fatima Al-Hassan | Platform Engineering | P1 | Open |  | T+15
ACT-011 | Diagnosis | Check recent change/deployment history (last 4 hours) | Fatima Al-Hassan | Platform Engineering | P1 | Open |  | T+15
ACT-012 | Diagnosis | Document working hypothesis in Slack channel | Daniel Ortega | SRE | P2 | Open |  | T+20
ACT-013 | Containment | Execute primary containment action (per diagnosis findings) | Fatima Al-Hassan | Platform Engineering | P1 | Open |  | T+20
ACT-014 | Containment | Validate containment effectiveness — monitor error rates | Fatima Al-Hassan | Platform Engineering | P1 | Open |  | T+30
ACT-015 | Containment | Document all actions taken with exact timestamps in Slack | Fatima Al-Hassan | Platform Engineering | P2 | Open |  | T+35
ACT-016 | Resolution | Validate Global Application Network — All Customer-Facing Traffic end-to-end health checks pass | Daniel Ortega | SRE | P1 | Open |  | T+0 post-fix
ACT-017 | Resolution | Confirm error rate and latency return to baseline | Daniel Ortega | SRE | P1 | Open |  | T+5 post-fix
ACT-018 | Resolution | Run synthetic monitor / smoke test | Daniel Ortega | SRE | P1 | Open |  | T+5 post-fix
ACT-019 | Resolution | Formally downgrade to Sev2 / close bridge once all checks pass | Daniel Ortega | SRE | P2 | Open |  | T+10 post-fix
ACT-020 | Resolution | Send Service Restored notification (Email Template 5) | Daniel Ortega | SRE | P1 | Open |  | T+5 post-fix
ACT-021 | Resolution | Update ServiceNow incident ticket with timeline and resolution | Daniel Ortega | SRE | P2 | Open |  | T+30 post-fix
ACT-022 | Resolution | Create PIR ticket and schedule PIR meeting | Daniel Ortega | SRE | P2 | Open |  | T+2 days
ACT-023 | Resolution | Send PIR invitation email (Template 6) | Carlos Mendez | Engineering Leadership | P2 | Open |  | T+1 day

## Escalation Log
Time (UTC) | Contact Name | Role | Method | Topic | Response | Next Action
| Daniel Ortega | Incident Commander | Phone + Slack + Email
| Fatima Al-Hassan | Technical Lead | Phone + Slack + Email
| Carlos Mendez | Communications Lead | Phone + Slack + Email
| Aisha Nwosu | On-Call Engineer | Phone + Slack + Email
| Wei Zhang | On-Call Engineer | Phone + Slack + Email
| NOC Bridge Coordinator | NOC Lead | Phone + Slack + Email
| Sandra Kowalski | Customer Impact Lead | Slack + Email
| Ravi Krishnamurthy | Product Lead | Slack + Email
| Ingrid Larsson | Security Lead | Slack + Email
| Marcus Webb | Legal and Compliance Lead | Slack + Email
| Eleanor Tran | Executive Sponsor | Slack + Email
| Bernard Osei | Executive Sponsor | Slack + Email
| Helena Vasquez | Executive Sponsor | Slack + Email

## Incident Timeline
Time (UTC) | Event Type | Event Description | Logged By | Evidence / Link
2026-02-26 09:12:37 UTC | Incident Detected | BGP sessions dropped on core-router-edge-01 at 09:12 UTC. All three upstream transit providers (Cogent, Zayo, Lumen) withdrew routes simultaneously. Customer-facing services globally unreachable. | PagerDuty Auto-Alert (BGP peer down — 3 simultaneous peers)
2026-02-26 09:14:00 UTC | Incident Opened | INC0091245 declared Sev1 | Network Operations
[T+0] | IC Engaged | Daniel Ortega joined as Incident Commander | Daniel Ortega
[T+0] | Bridge Opened | Zoom bridge opened: https://corp.zoom.us/j/82345678901?pwd=WarRoom2026! | Daniel Ortega | https://corp.zoom.us/j/82345678901?pwd=WarRoom2026!
[T+0] | Slack Channel Created | Incident channel created: #incinc0091245

## Summary Dashboard
INCIDENT SUMMARY DASHBOARD
INCIDENT DETAILS
Incident Number | INC0091245
Title | Multi-Region Network Outage — BGP Route Withdrawal Causing Global Connectivity Loss
Severity | 1 - Critical
Priority | 1 - Critical
State | In Progress
Affected Service | Global Application Network — All Customer-Facing Traffic
Affected CI | core-router-edge-01
Environment | Production (global (us-east-1, eu-west-1, ap-southeast-1))
Business Impact | All inbound customer traffic to production services is failing. 100% packet loss from external clients to all three production regions. Estimated 45,000 active sessions dropped. Revenue impact ~$120K/minute. B2B SLA breach imminent for Tier-1 enterprise customers. Brand and regulatory exposure if outage exceeds 30 minutes.
Opened At | 2026-02-26 09:14:00 UTC
Detected At | 2026-02-26 09:12:37 UTC
Resolved At | [TO BE FILLED]
Total Duration | [TO BE FILLED]
WAR ROOM
Incident Commander | Daniel Ortega ¦ +1-415-555-0101 ¦ @daniel.ortega
Technical Lead | Fatima Al-Hassan ¦ +1-415-555-0102 ¦ @fatima.alhassan
Zoom Bridge | https://corp.zoom.us/j/82345678901?pwd=WarRoom2026!
Slack Channel | #incinc0091245
Assignment Group | NOC — Tier 3 Network Engineering
ACTION TRACKER SUMMARY (LIVE)
Total Actions | =COUNTA('Action Items'!A2:A1000)-COUNTBLANK('Action Items'!A2:A1000)
Open Actions | =COUNTIF('Action Items'!G2:G1000,"Open")
In Progress | =COUNTIF('Action Items'!G2:G1000,"In Progress")
Completed | =COUNTIF('Action Items'!G2:G1000,"Done")
Blocked | =COUNTIF('Action Items'!G2:G1000,"Blocked")
% Complete | =IFERROR(TEXT(COUNTIF('Action Items'!G2:G1000,"Done")/COUNTA('Action Items'!A2:A1000)*100,"0.0")&"%","0%")
STAKEHOLDER QUICK REFERENCE
Daniel Ortega (Incident Commander) | +1-415-555-0101 ¦ d.ortega@corp.example.com ¦ @daniel.ortega
Fatima Al-Hassan (Technical Lead) | +1-415-555-0102 ¦ f.alhassan@corp.example.com ¦ @fatima.alhassan
Carlos Mendez (Communications Lead) | +1-415-555-0103 ¦ c.mendez@corp.example.com ¦ @carlos.mendez
Aisha Nwosu (On-Call Engineer) | +1-415-555-0104 ¦ a.nwosu@corp.example.com ¦ @aisha.nwosu
Wei Zhang (On-Call Engineer) | +1-415-555-0105 ¦ w.zhang@corp.example.com ¦ @wei.zhang
NOC Bridge Coordinator (NOC Lead) | +1-415-555-0199 ¦ noc-oncall@corp.example.com ¦ @noc-oncall
Sandra Kowalski (Customer Impact Lead) | +1-415-555-0201 ¦ s.kowalski@corp.example.com ¦ @sandra.kowalski
Ravi Krishnamurthy (Product Lead) | +1-415-555-0202 ¦ r.krishnamurthy@corp.example.com ¦ @ravi.krishnamurthy
Ingrid Larsson (Security Lead) | +1-415-555-0203 ¦ i.larsson@corp.example.com ¦ @ingrid.larsson
Marcus Webb (Legal and Compliance Lead) | +1-415-555-0204 ¦ m.webb@corp.example.com ¦ @marcus.webb
Eleanor Tran (Executive Sponsor) | +1-415-555-0301 ¦ e.tran@corp.example.com ¦ @eleanor.tran
Bernard Osei (Executive Sponsor) | +1-415-555-0302 ¦ b.osei@corp.example.com ¦ @bernard.osei
Helena Vasquez (Executive Sponsor) | +1-415-555-0303 ¦ h.vasquez@corp.example.com ¦ @helena.vasquez
VENDOR ESCALATIONS
AWS Support — P1 - Production System Down | Account: AWS-112233445566 ¦ Phone: +1-888-280-4331
Cloudflare Enterprise — Business Critical | Account: CF-ENT-998877 ¦ Phone: +1-650-319-8930
Stripe Support — P1 - Production Incident | Account: STR-acct-1A2B3C4D5E6F ¦ Phone: +1-888-963-8220
Oracle Support — SEV1 - Production Down | Account: ORA-77665544 ¦ Phone: +1-800-223-1711
PagerDuty Support — Critical | Account: PD-ENT-CORP2026 ¦ Phone: +1-415-990-9199
Generated By | MIM-Runbook Generator — 2026-02-26 12:35:39 UTC